## Gantt Chart Template
Note that this timeline PhD depicts a FT 3 year timeline. This candidate is a PT student and therefore is on an extended 7 year timeline.
[5 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
TASK TITLE | START DATE | DUE DATE | DURATION | PCT COMPLETE | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Situating, defining and interviewing
Reading and situating research | 2021-02-09 | 2022-02-09 | 360 | 65% | bar: Q1 Feb to Q1 Feb
Project approval | 2021-02-09 | 2021-08-08 | 179 | 100% | bar: Q1 Feb to Q3 Aug
Preparing and testing interviews | 2021-09-01 | 2021-12-31 | 120 | 0% | bar: Q3 Sep to Q4 Dec
Observation of design in chosen OSS & HOSS projects | 2021-09-01 | 2026-01-31 | 1590 | 0% | bar: Q3 Sep to Q1 Jan
Interviews: Humanitarian orgs | 2021-01-09 | 31/09/22 | 1590 | 0% | bar: Q3 Sep to Q3 Sep
Interviews: Designers in OSS | 2021-09-01 | 2022-09-30 | 389 | 0% | bar: Q3 Sep to Q3 Sep
Interviews: Designers in humanitarian org | 2021-09-01 | 2022-09-30 | 389 | 0% | bar: Q3 Sep to Q3 Sep
Interviews: Beneficiaries of chosen humanitarian OSS | 2021-09-01 | 2022-09-30 | 389 | 0% | bar: Q3 Sep to Q3 Sep
Coding and analysis of interviews | 2022-10-01 | 2022-11-30 | 59 | 0% | bar: Q4 Oct to Q4 Nov
Coding and analysis of HOSS observation | 2022-10-01 | 2022-11-30 | 59 | 0% | bar: Q4 Oct to Q4 Nov
Annual progression | 2022-12-01 | 2022-12-31 | 30 | 0% | bar: Q4 Dec
Fieldwork 1
Prepare fieldwork 1 | 2023-01-01 | 2023-05-30 | 149 | 0% | bar: Q1 Jan to Q2 May
Fieldwork 1 | 2023-01-06 | 2024-03-30 | 444 | 0% | bar: Q2 Jun to Q1 Mar
Fieldwork 1 analysis | 2024-04-01 | 2024-07-30 | 119 | 0% | bar: Q2 Apr to Q3 Jul
Coding and analysis of HOSS observation | 2024-04-01 | 2024-07-30 | 119 | 0% | bar: Q2 Apr to Q3 Jul
Annual progression | 2024-08-01 | 2024-09-01 | 30 | 0% | bar: Q3 Aug
Field work 2
Prepare fieldwork 2 | 2024-07-01 | 2024-11-30 | 149 | 0% | bar: Q3 Jul to Q4 Nov
Fieldwork 2 | 2024-12-01 | 2025-08-30 | 269 | 0% | bar: Q4 Dec to Q3 Sep
Fieldwork 2 analysis | 2025-10-01 | 2026-01-31 | 120 | 0% | bar: Q4 Oct to Q1 Jan
Coding and analysis of HOSS observation | 2025-10-01 | 2026-01-31 | 120 | 0% | bar: Q4 Oct to Q1 Jan
Writing up
Writing up thesis | 2026-02-01 | 2028-01-31 | 720 | 0% | bar: Q1 Feb to Q1 Jan
Thesis submission | 2028-02-01 | 2028-02-29 | 28 | 0% | bar: Q1 Feb
Onoging tasks
Literature reviews | 2021-02-09 | 2027-12-31 | 2482 | 0% | bar: Q1 Feb to Q4 Dec
Diary and autoethnography | 2021-02-09 | 2027-12-31 | 2482 | 2% | bar: Q1 Feb to Q4 Dec
Budget | Estimated | Actual
Interview transcriptions | £500
Translation costs for consent forms | £20 per A4 page
Interviewee participation fees | 50 x £25 = 1250
Fieldwork 1 expenses | £1500
Fieldwork 2 expenses | £1500
Conference attendance | £1000

## Copy of Gantt Chart Template
Note that this timeline PhD depicts a FT 3 year timeline. This candidate is a PT student and therefore is on 7 year timeline.
[5 empty] | 2021 | [14 empty] | 2022 | [14 empty] | 2023 | [14 empty] | 2024
TASK TITLE | START DATE | DUE DATE | DURATION | PCT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Project Conception and Initiation
Project Charter | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
Project Charter Revisions | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W
Research | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
Projections | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
Stakeholders | 2018-03-18 | 2018-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
Guidelines | 2018-03-19 | 2018-03-22 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
Project Initiation | 2018-03-23 | 2018-03-23 | 0 | 50% | bar: WEEK 3 F
Project Definition and Planning
Scope & Goal Setting | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
Budget | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
Communication Plan |  |  | 0 | 0%
Risk Management |  |  | 0 | 0%
Project Launch & Execution
Status & Tracking |  |  | 0 | 0%
KPIs |  |  | 0 | 0%
Monitoring |  |  | 0 | 0%
Forecasts |  |  | 0 | 0%
Project Updates |  |  | 0 | 0%
Chart Updates |  |  | 0 | 0%
Project Performance/Monitoring
Project Objectives |  |  | 0 | 0%
Quality Deliverables |  |  | 0 | 0%
Effort & Cost Tracking |  |  | 0 | 0%
Project Performance |  |  | 0 | 0%
Budget